## Sheet1
Planned Sprint | Actual Sprint | User ID | User Story Description | MOSCOW | Dependency | Assigned | Status
Sprint 1 | Sprint 1 | US-001 | Setup project environment (JDK, IntelliJ, GitHub) Install JDK: Download and install the correct Java Development Kit version on all developer machines. Configure IntelliJ: Set up IntelliJ IDEA with project structure, required plugins, and coding settings. Setup GitHub: Initialize a repository, configure Git for version control, and ensure team collaboration access. | MUST HAVE | None | Amitha P | 3- Completed
Sprint 1 | Sprint 1 | US-002 | Implement Product model & InventoryManager with OOP + Exception Handling .Design the Product class with necessary attributes, implement the InventoryManager class with CRUD methods using OOP principles, and add proper exception handling for invalid inputs and errors. | MUST HAVE | Depends on US-001 | Amitha P | 3- Completed
Sprint 1 | Sprint 1 | US-003 | Implement persistence with CSV & Git workflow Create CSV files to store product data, implement read/write operations for persistence, and manage code changes with Git workflow. | MUST HAVE | Depends on US-002 | Amitha P | 3- Completed
Sprint 1 | Sprint 1 | US-004 | Database basics: SQL practice + JDBC connection test Set up sample database tables, practice basic SQL CRUD queries, and test JDBC connection from Java application. | MUST HAVE | Depends on US-003 | Amitha P | 3- Completed
Sprint 2 | Sprint 2 | US-005 | Implement Read Operations (getAll, getById) & Console Menu Integration Implement getAll and getById methods, integrate them into console menu, and ensure proper display of data. | MUST HAVE | Depends on US-004 | Amitha P | 3- Completed
Sprint 2 | Sprint 2 | US-006 | Implement Update & Delete Operations Add methods for updating and deleting records, handle errors for invalid inputs, and test operations through console menu. | MUST HAVE | Depends on US-005 | Amitha P | 3- Completed
Sprint 2 | Sprint 2 | US-007 | Integrate CRUD into Console Menu (End-to-End Test) Combine all CRUD methods into menu options, test workflows end-to-end, and handle user input errors gracefully. | MUST HAVE | Depends on US-006 | Amitha P | 3- Completed
Sprint 2 | Sprint 2 | US-008 | Add Input Validation & Error Handling Validate all user inputs in console menus, handle exceptions for invalid or missing data, and provide clear error messages. | MUST HAVE | Depends on US-007 | Amitha P | 3- Completed
Sprint 2 | Sprint 2 | US-009 | JUnit testing Write unit tests for Product and InventoryManager methods, test CSV and database operations, and ensure all edge cases are covered. | MUST HAVE | Depends on US-008 | Amitha P | 3- Completed
Sprint 3 | Sprint 3 | US-010 | Implement CSVHelper for exporting inventory data Create CSVHelper class, implement export methods, and test file generation with proper formatting. | MUST HAVE | Depends on US-009 | Amitha P | 3- Completed
Sprint 3 | Sprint 3 | US-011 | Implement EmailService to send reports via SMTP Set up EmailService class, configure SMTP settings, and send automated reports via email. | MUST HAVE | Depends on US-010 | Amitha P | 3- Completed
Sprint 3 | Sprint 3 | US-012 | Add “Generate Report” option in Admin Menu Add menu option for report generation, link it to CSVHelper and EmailService, and display confirmation messages. | SHOULD HAVE | Depends on US-011 | Amitha P | 3- Completed
Sprint 3 | Sprint 3 | US-013 | Integrate DB + CSV + Email modules for full reporting Combine database, CSV export, and email modules, ensure seamless reporting, and test complete workflow. | MUST HAVE | Depends on US-012 | Amitha P | 3- Completed
Sprint 3 | Sprint 3 | US-014 | Implement OTP-based user verification during registration Generate OTP for new users, send via email, and validate OTP during registration. | SHOULD HAVE | Depends on US-013 | Amitha P | 3- Completed
Sprint 3 | Sprint 3 | US-015 | Add “Verify Email” & “Resend OTP” options in main menu Provide options for verifying email, resending OTP, and handling invalid or expired codes. | COULD HAVE | Depends on US-014 | Amitha P | 3- Completed
Sprint 4 | Sprint 4 | US-016 | Implement stock monitoring logic for low-stock alerting Check inventory levels against thresholds, flag low-stock products, and prepare notifications. | MUST HAVE | Depends on US-015 | Amitha P | 3- Completed
Sprint 4 | Sprint 4 | US-017 | Develop and schedule automated stock alert generator Create scheduled tasks for stock alerts, generate reports automatically, and log alerts. | MUST HAVE | Depends on US-016 | Amitha P | 3- Completed
Sprint 4 | Sprint 4 | US-018 | Integrate email notifications for low-stock products Link low-stock alerts to EmailService, send automatic notifications, and confirm delivery. | MUST HAVE | Depends on US-017 | Amitha P | 3- Completed
Sprint 4 | Sprint 4 | US-019 | Package and deploy full inventory management system Build project package, include all modules, and deploy application for production use. | MUST HAVE | Depends on US-018 | Amitha P | 3- Completed